## Sheet1
Risk | Affects | Description | What would Batman do? | Risk Type | Probability | Effects
Member drops the class | Project | A group member decides to drop the class for personal reasons | Ensure there is overlap of reponsibilities between team members so multiple people understand each other's job. Shuffle team repsonsibilites to distribute the person's work out evenly/fairly | People | Low | Tolerable
Time required to develop software is underestimated | Project | We messed up in deciding timelines, our abilities to piece together the app, or underestimated the complexity of interactions | Cry. Then proceed to find alternative pathways to complete the app. Burn the midnight oil if allowed. Speak to the professor if there could be some leeway or specification changes | Estimation | Moderate | Catastrophic
Website rejects web scraping usage | Product and Project | The target website rejects usage of web scraping tools | Find alternative web image sites. If none allow web scraping, change core technology to API usage. | Tools | Low | Serious
Someone's computer dies | Project | A group member's computer dies and stops working | Have constant github pushes (not to main) so we have a recoverable source code up to a point (mitigates loss). | Technology | Moderate | Insignificant
Technology changes to newer ver. | Business?? | Technology used becomes obsolete | Change core technologies to use usable frameworks if old one cannot be used. | Tools | Low | Insignificant
Core technologies don't communicate in the expected way | Product and Project | JavaFX and Jsoup do not interact in the way we expect them to | Find workarounds. Change code so that the interaction is more simplistic and direct. If need be, change one of the technologies to one that is more compatible with the other. | Tools | Low | Serious
Scene Builder is inadequate | Product and Project | Scene Builder does an inadequate job in creating a sufficient UI/UX | Write handwritten code or search for open-source/free solutions on the internet | Tools | Moderate | Tolerable
Group member goes dark | Project | A member of the group stops communicating with the group. The group is in the dark about the work done and the person's commitment to the project | Contact the professor that a student may be having personal events in his or her life preventing them from working on the project and communicating with us. Create a deadline for communication, and if not met, split up the person's work accordingly | People | Low | Serious
Someone gets sick | Project | Someone gets sick =( | Contact the person and see if they need to have their workload aleviated or shifted. If they need help with workload, distribute work evenly to other members in the group. To reduce the risk, encourage everyone to follow safety protocols in today's society. | People | Moderate to High | Tolerable